## Sheet1
Sr no | Type | Raised By | Date of Reporting | Company | Project | Task | Priority | Done By | Date of Release | Pending | UAT | Post UAT Issues | Released/ Confirmed | Remarks
1 | Bug | Rishit | 2017-08-01 | EAT | EAT ERP | Loading Time of Sales Page | High | Prasad | 2017-08-24 | 1 | 2017-08-24
2 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Date sort on all columns in data table | High | Prasad | 2017-08-24 | 1 | 2017-08-24
3 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Display only sales representative name in dropdown in new sales entry | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
4 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Scroll issue in sales module | High | Prasad | 2017-08-24 | 1 | 2017-08-24
5 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Make Invoice icon big | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
6 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Tag state codes for all distributors | High | Prasad | 2017-08-24 | 1 | 2017-08-24
7 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Check for error when invoice made inactive | High | Prasad | 2017-08-26 | 1 | 2017-08-26
8 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Loading time of sales sku report | High | Dhaval | 2017-08-28 | 0 | 2017-08-28
9 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Remove Product expired and sample from sales report | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
10 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Remove all data from cancelled except invoice number sales invoice report | High | Dhaval | 2017-08-24 | 1 | 2017-08-24 | 2017-08-30
11 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Date format in all reports | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
12 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Sort date of processing wise in sales report | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
13 | New | Rishit | 2017-08-23 | EAT | EAT ERP | Maker and Checker for sales module on creation of sales order | High | Prasad | 2017-08-26 | 1 | 2017-08-26 | 2017-08-30
14 | New | Rishit | 2017-08-23 | EAT | EAT ERP | Creation of voucher code for sales return | High | Prasad | 2017-08-26 | 1 | 2017-08-26
15 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Remove Cancelled invoices from Sales SKU report | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
16 | Bug | Rishit | 2017-08-23 | EAT | EAT ERP | Dashboard Sales in bar | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
17 | Bug | Rishit | 2017-08-24 | EAT | EAT ERP | Product exchange should not be tagged under “Sale” | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
18 | Bug | Rishit | 2017-08-24 | EAT | EAT ERP | product expired should be marked under Product expired only not in sample | High | Dhaval | 2017-08-24 | 1 | 2017-08-24
19 | New | Rishit | 2017-08-30 | EAT | EAT ERP | Include Area in all sales report | High | Dhaval | 2017-08-31 | 1 | 2017-08-31
20 | Bug | Rishit | 2017-08-30 | EAT | EAT ERP | Sales Invoice in same format according to sales sku report | High | Dhaval | 2017-08-31 | 1 | 2017-08-31
21 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Page to add amazon fees and add to credit note | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
22 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Promoter Stock report rename to Promoter Sale | High | Dhaval | 2017-09-08 | 1 | 2017-09-08
23 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Remove Sales Invoice report | High | Dhaval | 2017-09-08 | 1 | 2017-09-08
24 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Rename sales invoice sku recipe to sales report | High | Dhaval | 2017-09-08 | 1 | 2017-09-08
25 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Rename Promoter stock report to Promoters sales report | High | Dhaval | 2017-09-08 | 1 | 2017-09-08
26 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Change sequence for report | High | Dhaval | 2017-09-08 | 1 | 2017-09-08
27 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Remove promoter from sales representative list in reports | High | Dhaval | 2017-09-08 | 1 | 2017-09-08
28 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Add closing stock in sales representative location report | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
29 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Show popup as please switch on gps for geolocation if gps off for 3 times | High | Dhaval | 2017-09-08 | 0 | 2017-09-08
30 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Task list for sales representative for follow ups | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
31 | New | Rishit | 2017-09-05 | EAT | EAT ERP | Order no for amazon to be in same format as of amazon | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
32 | New | Rishit | 2017-09-05 | EAT | EAT ERP | In Aeging report remove sample and product expired | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
33 | New | Rishit | 2017-09-06 | EAT | EAT ERP | In Aeging report add area and location | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
34 | New | Rishit | 2017-09-07 | EAT | EAT ERP | Delivery person login with order status and geo tagging | High | Dhaval | 2017-08-13 | 0 | 2017-08-13
35 | New | Rishit | 2017-09-15 | EAT | EAT ERP | Add mt list to SR | High |  |  | 0